## START HERE
KASA CORE — MASTER TASK TRACKER
Tɛkyerɛma Pa Hackathon 2026 · prototype sprint 6–22 Sept · second screening 23–24 Sept · top 25 on 26 Sept
HOW TO USE THIS WORKBOOK
1. Find your tasks on the 'Task Tracker' sheet — filter the Owner column to your name.
2. Each morning, update ONLY the Status column of your tasks. That is the whole discipline.
3. Status options: Not started · In progress · Blocked · Done. If Blocked, say why in Comments and shout in the group.
4. 'Depends On' = do not start until that task is Done. 'Feeds Into' = someone is waiting on you.
5. 'Person Dashboard' auto-counts your progress. 'Milestones' are fixed dates — nothing moves them.
6. 'Submission Checklist' is what must be true to present on 23 Sept. That is the finish line.
THE CHAIN IN ONE SENTENCE
Prove USSD works (Days 1–3) → join one full voice→intent→confirm→USSD→PIN→result path (by Day 8) → add symbol board + data intent + accessibility (by Day 12) → test with blind users, record backup, rehearse (by Day 15) → present.
THE ONE RULE THAT MATTERS MOST
We build in parallel by mocking at the seams. Nobody waits. Build against a fake of whatever isn't ready yet, swap it for the real thing when it lands. Contracts are in docs/00_START_HERE.md.
NON-NEGOTIABLE: we never hold the user's PIN. Frederick needs a real Android phone + MTN SIM from Day 1 or the whole build is blocked.

## Task Tracker
Task ID | Phase | Owner | Task | Deliverable / Evidence | Start | Due | Depends On | Feeds Into | Priority | Status | Comments
K01 | Setup · Day 1 | Frederick Kankam | Secure a real Android phone with an active MTN SIM for USSD testing | Phone in hand, confirmed in chat | Day 1 | Day 1 | - | K10,K11 | Critical | Not started
K02 | Setup · Day 1 | Frederick Kankam | Create GitHub repo, add everyone, push the starter repo (code + docs) | Repo URL shared; all 5 have access | Day 1 | Day 1 | - | ALL | Critical | Not started
K03 | Setup · Day 1 | All members | Everyone reads docs/00_START_HERE.md and their own role guide | Confirmed in standup | Day 1 | Day 1 | K02 | ALL | Critical | Not started
K04 | Setup · Day 1 | All members | Install toolchain (Python+FastAPI / Android Studio+Kotlin / ngrok) | Screenshot in chat | Day 1 | Day 1 | K02 | - | High | Not started
K05 | Setup · Day 1 | Frederick Kankam | First design session: lock PIN-entry mechanism, wake method, contacts source | Decisions in dev log | Day 1 | Day 1 | K03 | K30,K41 | High | Not started
K10 | Spike · Days 1–3 | Frederick Kankam | Dial *170# and map the real MTN menu tree into config/ussd_scripts.json | Verified menu digits committed | Day 1 | Day 2 | K01 | K12,K31 | Critical | Not started
K11 | Spike · Days 1–3 | Frederick Kankam | Balance via sendUssdRequest reads the real balance aloud on device | Working balance path (video) | Day 1 | Day 2 | K01 | K33 | Critical | Not started
K12 | Spike · Days 1–3 | Frederick Kankam | AccessibilityService drives 2–3 send-money steps + detects PIN prompt on 2 phones | Spike demo on 2 devices | Day 2 | Day 3 | K10 | K31 | Critical | Not started
K13 | Spike · Days 1–3 | Frederick Kankam | GO / NO-GO decision on interactive USSD (else switch to assisted mode) | Written decision in dev log | Day 3 | Day 3 | K12 | K31 | Critical | Not started
K20 | Server · Days 1–3 | Selorm Sem | Stand up FastAPI, /health live, ngrok URL shared with Richmond | /health returns ok from phone | Day 1 | Day 1 | K02 | K21,K42 | Critical | Not started
K21 | Server · Days 1–3 | Selorm Sem | Extract parser into intent_parser.py; expand Twi grammar (actions, numbers, recipients) | 20 typed commands parse correctly | Day 1 | Day 3 | K20 | K22,K23 | High | Not started
K30 | Speech · Days 1–3 | Kelvin Agyare Yeboah | Email Evans + lab for dcshcilab_Whisper/Vits + datasets; set Whisper-small fallback | Emails sent; baseline ASR runs | Day 1 | Day 1 | K03 | K32,K34 | High | Not started
K31 | Speech · Days 1–3 | Kelvin Agyare Yeboah | run_asr(bytes)->str baseline handed to Selorm (unblocks the pipeline) | Function importable in server | Day 1 | Day 2 | K30 | K22 | High | Not started
K40 | App · Days 1–3 | Richmond Nyamedor | Kotlin project runs on device; permissions; minSdk 26 | App installs and launches | Day 1 | Day 1 | K02 | K41,K42 | High | Not started
K41 | App · Days 1–3 | Richmond Nyamedor | Network layer + FakeApi + FakeUssdEngine so UI builds with no server/engine | Flow runs on canned Intents | Day 1 | Day 3 | K40 | K43 | High | Not started
K22 | Server · Days 4–8 | Selorm Sem | /understand endpoint = transcribe + parse in one call | Returns Intent from audio | Day 4 | Day 5 | K21,K31 | K43 | High | Not started
K23 | Server · Days 4–8 | Selorm Sem | LLM fallback constrained to JSON + schema validation (safe re-ask on failure) | Missed phrasings parse; bad output re-asks | Day 4 | Day 6 | K21 | - | Normal | Not started
K32 | Speech · Days 4–8 | Kelvin Agyare Yeboah | Collect ~25–30 min command audio; bias decoding to command vocabulary | Dataset + improved accuracy | Day 3 | Day 6 | K30 | K34 | High | Not started
K33 | Speech · Days 4–8 | Kelvin Agyare Yeboah | Pre-record fixed Twi prompts + number-to-Twi readback (say_amount_twi) | Prompt pack + readback working | Day 3 | Day 5 | K11 | K43 | High | Not started
K34 | Speech · Days 4–8 | Kelvin Agyare Yeboah | Fine-tune ASR on command audio if accuracy needs it | Better command accuracy (measured) | Day 6 | Day 8 | K32 | K43 | Normal | Not started
K31b | USSD · Days 4–8 | Frederick Kankam | State machine: confirmed Intent -> scripted USSD run (RealUssdEngine), fail-closed | send-money runs on device | Day 4 | Day 8 | K13 | K43 | Critical | Not started
K42 | App · Days 4–8 | Richmond Nyamedor | Build Home, Listening, Confirm, Result screens — each TalkBack-clean | 4 screens, TalkBack pass each | Day 2 | Day 7 | K20,K40 | K43 | High | Not started
K43 | Integration · Day 8 | All members | JOIN THE PATH: voice→/understand→Intent→confirm→RealUssdEngine→PIN→result on device | One full send-money end to end | Day 6 | Day 8 | K22,K31b,K42,K33 | K50 | Critical | Not started
K44 | App · Days 9–12 | Richmond Nyamedor | Symbol board builds the SAME Intent and enters the SAME confirm flow | Symbol path -> same Intent | Day 9 | Day 11 | K43 | K50 | High | Not started
K24 | Server · Days 9–12 | Selorm Sem | buy_data intent + audit log/receipt endpoint (action only, no PIN/audio) | Data intent parses; receipt returns Twi summary | Day 9 | Day 11 | K22 | K50 | Normal | Not started
K45 | App · Days 9–12 | Richmond Nyamedor | Accessible PIN keypad (haptic, never announces digit, never stored) | Keypad usable eyes-off | Day 9 | Day 11 | K43 | K50 | High | Not started
K46 | App · Days 9–12 | Richmond Nyamedor | Accessibility polish: no-timeout, contrast>=4.5:1, captions, service-enable onboarding | Full WCAG-AA pass on core flow | Day 10 | Day 12 | K42 | K50 | High | Not started
K35 | Speech · Days 9–12 | Kelvin Agyare Yeboah | Subgroup evaluation (speaker/amount/mic/noise/code-switch); fix worst subgroup | Accuracy table; improved weak subgroup | Day 9 | Day 12 | K34 | K51 | Normal | Not started
K32b | USSD · Days 9–12 | Frederick Kankam | Add buy-data flow; harden fail-closed on unexpected menus; test on multiple phones | Data flow works; safe on mismatch | Day 9 | Day 12 | K31b | K50 | Normal | Not started
K50 | Test · Days 13–15 | Accessibility Lead | User testing with 2–3 blind users on real tasks; log every point they get stuck | Testing notes + change log | Day 13 | Day 14 | K43,K44,K45,K46 | K51 | Critical | Not started
K51 | Test · Days 13–15 | All members | Fix what testing broke; adversarial tests (silence, wrong name, network drop) | Failures degrade safely, no crashes | Day 13 | Day 15 | K50 | K53 | High | Not started
K52 | Test · Days 13–15 | Frederick Kankam | Record a backup screen-capture of a full successful real run | Backup video saved | Day 13 | Day 14 | K43 | K53 | Critical | Not started
K53 | Present · Days 13–15 | Frederick Kankam | Write + rehearse the 5-min presentation (narrator + phone driver); time it x3 | Rehearsed deck + demo script | Day 14 | Day 15 | K51,K52 | K60 | High | Not started
K54 | Present · Days 13–15 | Accessibility Lead | Prepare the one-line user-testing evidence ('we changed X after Y') | Evidence line agreed | Day 14 | Day 15 | K50 | K60 | High | Not started
K60 | Present · 23–24 Sept | All members | Deliver the live prototype presentation to the mentors | Presentation done | Day 16 | Day 17 | K53,K54 | (final) | Critical | Not started

## Person Dashboard
PROGRESS BY PERSON (auto-updates from Task Tracker)
Member | Squad | Total | Done | In progress | Blocked | Not started | % Complete
Frederick Kankam | USSD / Integration
Selorm Sem | Server / NLU
Kelvin Agyare Yeboah | Speech (ASR/TTS)
Richmond Nyamedor | App / Accessibility
Accessibility Lead | Inclusion / QA
TEAM

## Milestones
FIXED CHECKPOINTS — nothing moves these
By | Phase | Milestone | What must be true | Accountable
Day 1 | Setup | Kickoff + repo + design session | Roles set, repo live, PIN/wake/contacts decided, phone+SIM secured | Frederick
Day 3 | Spike | USSD GO/NO-GO | Balance reads aloud; interactive USSD proven on 2 phones OR assisted mode chosen | Frederick
Day 3 | Spike | Pipeline unblocked | /health live, baseline ASR handed over, app builds on fakes | Selorm
Day 8 | Integration | THIN PATH JOINED | One full send-money: voice→intent→confirm→USSD→user PIN→result on a real phone | All
Day 12 | Breadth | Feature complete | Symbol board + buy-data + full accessibility (TalkBack, no-timeout, captions, keypad) | Richmond
Day 14 | Test | User-tested | 2–3 blind users completed tasks; change log written; backup video recorded | Accessibility Lead
Day 15 | Rehearse | Demo-ready | Fixes in; adversarial tests pass safely; 5-min presentation rehearsed x3 | Frederick
23–24 Sept | Present | SECOND SCREENING | Live prototype presented to mentors | All
26 Sept | Result | Top 25 | Selection announced | -

## People & Roles
WHO OWNS WHAT
Member | Role | Squad | Owns (in one line)
Frederick Kankam | Project Lead + USSD Engineer | USSD / Integration | The risky module: driving USSD safely, PIN hand-off, architecture, standups, demo
Selorm Sem | Backend Engineer | Server / NLU | Inference server, Twi command parser, intent schema, audit log
Kelvin Agyare Yeboah | ML Engineer | Speech (ASR/TTS) | Twi speech-in and speech-out behind clean functions; fine-tuning; number-to-Twi
Richmond Nyamedor | Frontend (Android) Engineer | App / Accessibility | Native Kotlin app, screens, accessibility, capture, confirm, symbol board, PIN keypad
Accessibility Lead | Co-design + User Testing | Inclusion / QA | Owns PIN-entry decision, tests every screen, recruits blind testers, source of truth on Twi

## Submission Checklist
WHAT MUST BE TRUE TO PRESENT ON 23 SEPT
Requirement | Accountable | Done? | Evidence / location
Twi voice command is recognised and turned into a correct Intent | Selorm / Kelvin | No
Confirm-before-execute: app speaks + shows summary, waits for explicit approval | Richmond | No
Balance read back aloud in Twi on a real phone | Frederick / Kelvin | No
Send-money drives USSD and STOPS at the PIN for the user to enter (or assisted mode) | Frederick | No
PIN is never stored, never transmitted, never spoken | Frederick / Richmond | No
One non-transfer intent (buy data) works — proves it is not hard-coded | Selorm / Frederick | No
Symbol board produces the same Intent and confirm flow | Richmond | No
Usable with TalkBack, eyes-off, by a blind user | Richmond / Accessibility Lead | No
Captions on all spoken output; contrast and text size meet WCAG AA | Richmond | No
Works on a low-end phone over USSD (no dependency on good data) | Frederick | No
Command accuracy reported by subgroup, not one number | Kelvin | No
User-testing evidence: one concrete change made because a blind user asked | Accessibility Lead | No
Backup demo video of a full successful run recorded | Frederick | No
5-minute presentation rehearsed (narrator + phone driver) | Frederick | No